## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Discussion of the project | On 4th November we discuss the details regarding our project and work project is beyond QWERTY Form Filling project | Rishiraj Yadav | In discussion we discuss about the project how we are going to do in this project and what is the motive of our project and how it will help to others | MUST HAVE | no dependency | Rishiraj Yadav | 3- Completed
To create a road map | on 6th November we discussed the road map of everyone | Rishiraj Yadav | I represent my road map for the project how will I do things in my project | MUST HAVE | lucid chart | Rishiraj Yadav | 3- Completed
To add some innovative ideas in our project | on 8 November we give some more ideas to implement on our project | Rishiraj Yadav | I give the ideas to add FAQ part in our project and more I tools to make more easier to cancel the noises and etc | SHOULD HAVE | browser | Rishiraj Yadav | 3- Completed
Give the feedback of our mentor | on 11th November we give the feedback of our mentor | Rishiraj Yadav | I give my feedback regarding my mentor Vivek Gautam that he is good to explain the project and we are comfortable with him. | MUST HAVE | nodependency | Rishiraj Yadav | 3- Completed
Giving the case studies and our opinion regarding our project | on 12th November I give case study and some website link to my mentor | Rishiraj Yadav | I present the case studies explain about it and show the website of some form filling by using AI | SHOULD HAVE | browser | Rishiraj Yadav | 3- Completed
3 days to give the task | 2 day's it takes to complete the task and distribute with team. | Rishiraj Yadav | Giving the task document for regarding our group | MUST HAVE | on dependency | Rishiraj Yadav | 3- Completed
7 days plan to complete one week get and a certificate of python basic | 7 days it's taken , To completed all the task regarding the python. | Rishiraj Yadav | we started to discuss the python and doing coding in hackerrank to complete one week kit and give document | MUST HAVE | coding platform(Hackerrank) | Rishiraj Yadav | 3- Completed
7 days plan on discussing SQL and getting the certificate of basic SQL | 7 days its actually taken to complete all the things. | Rishiraj Yadav | In this week we started to discuss about the SQL and all the things which we can use in our project and complete the certification of SQL in this week i have to do | MUST HAVE | coding and discussion | Rishiraj Yadav | 3- Completed
7 Days discussion regarding the project for the model implement in the voice-to-text | one week discussing the queries and other things regarding the model | Rishiraj Yadav | In this week we discuss about the models for the voice-to-text and what model should be used in my project I am going to use OpenAi Whisper for model. and asking the problems related to the project and the things like error i facing in the project. | MUST HAVE | model integration | Rishiraj Yadav | 3- Completed
Note on F1: ====== ID#AAABYHlVm1U (2024-11-12 12:37:32) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Rishiraj Yadav | Beyond QWERTY:Form Filling project | I discussed the project with my mentor and he explain about it | 2024-11-04 | 2024-11-05 |  | Others | 3- Completed | 3
Rishiraj Yadav | Beyond QWERTY:Form Filling project | we represent the road map of our project | 2024-11-06 | 2024-11-07 |  | Others | 3- Completed | 5
Rishiraj Yadav | Beyond QWERTY:Form Filling project | we give the ideas to implement on our project to make it more advance and more interactive | 2024-11-08 | 2024-11-09 |  | Others | 3- Completed | 4
Rishiraj Yadav | Beyond QWERTY:Form Filling project | Explaining the case studies and some more website regarding the case study to understand the project | 2024-11-11 | 2024-11-18 |  | Others | 3- Completed | 7
Rishiraj Yadav | Beyond QWERTY:Form Filling project | To complete the one week kit preparation in hackerrank and get the python basic certificate and giving the documents of the code of hackerrank problem | 2024-11-18 | 2024-11-25 |  | Coding | 3- Completed | 7
Rishiraj Yadav | Beyond QWERTY:Form Filling project | completing the hackerrank exam to get the python basic certificate . |  | Unit Test |  | Unit Test | 3- Completed | 3
Rishiraj Yadav | Beyond QWERTY:Form Filling project | in this week I discussed the some of my doubt regarding SQL and creating the database on it and I created a document of SQL all the important questions with sir given the task ,and getting the SQL basic certificate from hackerrank. | 2024-11-26 | 2024-12-02 |  | Unit Test | 3- Completed | 4
Rishiraj Yadav | Beyond QWERTY:Form Filling project | In this week we get the task to discused about the models and it type which we implemented in the project and to get the accuracy of that model in the project | 2024-12-02 |  |  | Others | 3- Completed
Note on D2: ====== ID#AAABYHlVm1g Please enter the dates in either of these formats (2024-11-12 12:37:32) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABYHlVm2Y Please enter the dates in either of these formats (2024-11-12 12:37:33) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABYHlVm2M (2024-11-12 12:37:32) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABYHlVm1Y (2024-11-12 12:37:32) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABYHlVm1c (2024-11-12 12:37:32) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABYHlVm2U (2024-11-12 12:37:33) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABYHlVm2A (2024-11-12 12:37:32) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABYHlVm1s (2024-11-12 12:37:32) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABYHlVm2Q (2024-11-12 12:37:32) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABYHlVm2I (2024-11-12 12:37:32) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABYHlVm2E (2024-11-12 12:37:32) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABYHlVm1w (2024-11-12 12:37:32) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABYHlVm1k (2024-11-12 12:37:32) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABYHlVm10 (2024-11-12 12:37:32) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABYHlVm14 (2024-11-12 12:37:32) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABYHlVm1o (2024-11-12 12:37:32) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABYHlVm18 (2024-11-12 12:37:32) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 sprint | 1 | some new techniques like model using AI and some other model that make some entrance in our project but we overcome the model issues | we use whisper right now and it is giving accuracy , in future we going to use azure AI or OpenAi or acceptor different model but this type of model are paid software so we use whisper only
2 sprint | 2 | By using webpage storing the data of the user in the database it makes some error. | by discussing the errors with my mentor and after taking the help from online resources like chat GPT, Blackbox Ai and many other platforms to resolve this issue.
3 sprint | 3 | in redirecting of links from signup to login page and then go to the main index page it give me some problem | I resolve this error and I take the correct route in flask to redirect to correct page address on the basis of it URL.
4 sprint | 4 | In deployment which is good platform doubt and some of the error in the deployment because of not aligning the files correctly. | I discussed in group and with the mentor like we found a good platform for deployment and correctly align the files to deploy the project.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | discussion of the project(specific topic or field to make our voice from filling project) | 2024-04-11 | 14/11/2024 | Rishiraj , Harini , Nandini , Vaishnavi | we discuss about the project and then creating some road map and giving the case study or reading the document s |  |  | we completed our discussion about the project and get to the coding part
2 | Getting the information to make a webpage. | 18/11/2024 | 26/11/2024 | Rishiraj , Harini , Nandini , Vaishnavi |  |  |  | we completed our discussion about the project and get to the coding part
3 | adding the new features and some other things | 26/11/20204 | 2024-02-12 | Rishiraj , Harini , Nandini , Vaishnavi |  |  |  | we completed our discussion about the project and get to the coding part
4 | In diployment discussing about the platform for which is good and make it easier and faster. | 2024-04-12 | 2024-10-12 | Rishiraj , Harini , Nandini , Vaishnavi |  |  |  | we completed our discussion about the project and get to the coding part
5
6
7